## backlog
|  |  | As <WHO>, I want/need to <WHAT> so that <WHY>. |  |  |  | As <WHO>, I want/need to <WHAT> so that <WHY>.
WHO for the Role
NAME OF THE SOFTWARE: CheckMyZip |  |  | WHAT for Capability, Task, Hard-goal, and Soft-goal |  |  |  | WHO for the Role
|  |  | WHY for Task, Hard-goal, and Soft-goal |  |  |  | WHAT for Capability, Task, Hard-goal, and Soft-goal
Product owner: GOLDEN BAR | [6 empty] | WHY for Task, Hard-goal, and Soft-goal
Date of creation: 10/8/2019
ID | Name | Creation Date | Description | Size | Priority | Dependencies | Notes | Sprint | Responsibility
US1 | Finding database | 2019-08-10 | Finding database with the information app wants to provid user and list items. | Large | High |  | This will first need a survey to see what people might be interested in, then find out if those informations are available
US2 | Fetching data | 2019-08-10 | Fetch data from database and stroe in local database | large | High | backend | Determine if data should be stored or accessed form third party database per query
US3 | Analyze data | 2019-08-10 | Analyze data to summizing the data for each city | Large | High | US2 | Determine how to present data in picture, tabular form, graphs, charts etc
US4 | Login User | 10/14/2019 | Building a database which is storing users' account number. password, and other information. On one page, we need to provide the area which allows user to sign up a new account stored in user database, and to login the app.
US5 | Zip code | 10/14/2019 | Once user logged in, there is one page allowing users to enter zip code and the app return the information based on the zip code
US6 | Weather information | 10/14/2019 | By the each zip code, there is
US7 | Build maping page | 2019-08-10 | User should be able to see a map when they put in a more generic (City name, state, county name) information over specific zip code. | Large | Medium |  | This may be achieved: Build a map page which can link to google map. Get the GPS information from google maps.
US8 | Pop Notification about area | 2019-08-10 | Based on the gps information provided by google map. The app presents a pop up notification about recent news, crime rate, traffic and so on, about the area. | Medium | Medium | US4 | Using location technology
US9 | Display the weather information | 2019-08-10 | Based on the area location, the app present the average weather condition and temperature. | Small | Low | US2
US10 | Build fliter and checklist | 2019-08-10 | Build a fliter with check item, so user can select the information they want to know and narrow it down to their best interest | Large | Medium
US11 | Build a database store user information | 2019-08-10 | Build a database storing user account number, passwords, and other information. | Medium | High | US2
US12 | First page | 2019-08-10 | On the first page, there is a search bar that users can type in zip code or city name. After user click search buttom, next page will present the information of the city. | Medium | High
US13 | Handicap support | 2019-08-10 | If user is handicapped, location technology should be ale to tell them if they are side walks around, elevator in/out facilities and subway. | Large | Low | US9 | Will provide handicap support and make accesibility easier. It will also suggest areas with organizations that support specific conditions.
US14 | Find my commuinity | 2019-08-10 | Based on user info, including age, race, country of origin, stated interests, religion, and gender/sexuality, app will suggests unions, groups, organizations that provide support, and places of worship. | Medium | Medium | US9 | App will help user find people with common interest.
US15 | Area background check | 2019-08-10 | For user wanting to move, present relevant informations about areas they are interested in, including crime rate, school standing, average rent, level of education of residents, different demographics of the residents, Police ratings, health care facility ratings, access to transportation and number of commuters, and hospitals that could handle pre-existing conditions. | Large | High | US9 | Go into the database to get all information known about a specific zipcode, or extract data from bearue of statistics, and population census etc.
US16 | Comparing zip codes | 2019-08-10 | User check criterias and put in two zip codes. Results for both areas will be shown side by side. For example, user can compare school standings, and both results will be gathered and show to user. | Large | Medium | US9 | Given the criteria marked by user, app will provide the info on a tabular form comparing both areas.
US17 | Breaking news | 2019-08-10 | User will get pop up notifications of breaking news around the zipcode they provided as "home" | Large |  | US9 | This source for news using user zipcode, and presents it as a notification
US18 | Local Political representatives and their contact information | 2019-08-10 | User will be able to access a page with information of their political representatives | Large | Low | US3 | The information they can find will include name, picture if possible, office held, and contact information.
| Home page | 2019-08-10 | Home page should be intuitive. Icons should be so easy that non native speakers can navigate app. | Medium | High | US13 | Home page will include, profile, search bar, and notification.