## Sheet1
Sprint 1 backlog |  |  | GOLDEN BAR
ID | Name | Creation Date | Description | Size | Priority | Dependencies | Notes | Sprint | Responsibility
US1 | Account database | 10/15/2019 | Creating a database storing user information | medium | high |  |  | 1
US2 | Login User | 10/15/2019 | Building a database which is storing users' account number. password, and other information. On one page, we need to provide the area which allows user to sign up a new account stored in user database, and to login the app. | small | high | us1 |  | 1
US3 | User sign up | 10/15/2019 | Creating a page for user to sign up and storing the information to user databsae | small | high | us1
US4 | Enter zip codes | 10/15/2019 | An text box which allow user to enter zip code and return the information of the zip code | Large | high |  |  | 1
US5 | Home page | 10/15/2019 | Home page should be intuitive. Icons should be so easy that non native speakers can navigate app. | Medium | High |  | Home page will include, profile, search bar, and notification. | 1
US6 | Weather | 10/15/2019 | Using google API to provide the weather condition, include historical weather information and live weather. Historical weather condition includes average week, month, quater temparture. | Medium | medium |  |  | 1
US7 | Demographic information | 10/15/2019 | Data includes population, race, nation, and etc | Medium | medium |  |  | 1
US8 | Income | 10/15/2019 | The average income of the people living in the area | Medium | medium |  |  | 1
US9 | First page | 10/15/2019 | the first page of app | small | low |  |  | 1